Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after the final sprint for extra credit.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a real project, points are assigned via a game of "estimating poker" played by the entire team.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" - "Finished in Sprint 6" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that no duplicate work occurs, and that no tasks "fall through the cracks".

If you are wroking individually, you do NOT need to put your initials next to every task. We'll figure out who did the work. Somehow.
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the manual to cover this feature", or "Fix the seg fault bug".

Expect roughly 3 to 10 tasks per typical feature. Don't OVER plan, but also don't just write "Implement the feature". Find a middle ground. :-)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product Backlog
Product Name:	JADE Manager					Complete Fields in Green!!!
Team ID:	Hardik Patel

	Team Member Name					Initials	Student ID
Required	Hardik Patel					HP	1001533766

Sprint #	Remaining	Completed This Sprint			Comment
0	24			Total	Total number of features (in column H)
1	23	1		1	Total features left at the end of Sprint #1
2	20	3		2	Total features left at the end of Sprint #2
3	14	6		3	...and so on
4	13	1

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
	1	1	5	1	Finished in Sprint 1	Chess Player	Use a main window (GUI) with minimal menu bar only	Reduce training costs	Add Menubar with File > Exit
	2	1	3	1	Finished in Sprint 1	Chess Player	Start a new game	Play again and again and...
	3	2	13	2	Finished in Sprint 2	Chess Player	See an 8x8 game board of alternating colors	Feel comfortable playing a traditional game	Gtk::Grid of buttons, perhaps? Set background button colors for space, add game piece icon when occupied, blank otherwise
	4	2	13	2	Finished in Sprint 2	Chess Player	Be able to play with all of the standard pieces	Learn the traditional game with no changes	This probably requires a “Piece” abstract class from which “King”, Queen”, “Rook”, etc. derive, e.g., overriding the move() method. This is a pretty big (expensive) feature to implement.
	5	2	5	2	Finished in Sprint 2	Chess Player	See the location of each chess piece	Plan my next moves	Perhaps add game piece icon to button for any piece at this location
	6	3	3	3	Finished in Sprint 3	Chess Player	Select one of my game pieces to move	Start a move	Click the button, perhaps?
	7	3	13	3	Finished in Sprint 3	Chess Player	Select an empty square to which to move	End my move without a capture	Another click
	8	3	2	3	Finished in Sprint 3	Chess Player	Deselect a game piece that I had planned to move	Change my mind about moving it	Perhaps a tool bar button? Esc?
	9	3	5	3	Finished in Sprint 3	Chess Player	Select an opponent-occupied square for a capture	Capture my opponent’s pieces	This works for most pieces, but not pawns (I think?)
	10	3	5	3	Finished in Sprint 3	Chess Player	Know whose turn it is to move	Tell if I need to attempt a move or wait	Probably a status bar
	11	3	3	3	Finished in Sprint 3	Chess Player	See clear warnings if I attempt an illegal move	Learn the rules more thoroughly	Perhaps an error dialog, or other visual indication on the board
	12	4	8	4	Finished in Sprint 4	Chess Player	Perform a passing capture with a pawn	My pawns can be used offensively
	13	4	13			Chess Player	Perform a castle	Better protect my king with a rook
	14		5			Chess Player	Be able to declare a check	Warn my opponent their king is in danger	Perhaps a tool bar button? Or perhaps auto-detected?
	15		3			Chess Player	Be able to declare a checkmate	Win the game!	Something splashy, of course
	16		8			Chess Player	Save the game to a default file	Resume a game later
	17		8			Chess Player	Load the game from a default file	Resume a game later
	18					Chess Player	Undo a move	Correct a bad move	Not sure how to mechanize this if playing the computer, as it will make its move automatically without the human player’s input
	19					Chess Player	Redo a move	Reimplement a previous attempt if I can’t find a better alternative
	20					Chess Player	Save the game to a specified file	Resume one of many saved games later
	21					Chess Player	Load the game from a specified file	Resume one of many saved games later
	22					Chess Player	Receive a hint on my next move	Improve my game skills
	23					Chess Player	See all possible moves after selecting a piece	More easily evaluate and select a move	Perhaps change color of all squares accessible by the piece
	24					Chess Player	Perform a promotion	Promote my pawns to more powerful pieces
	25					Chess Player	Have a record of each game in standard notation	Brag about my wins and analyze my losses
Product Backlog Burn Chart
Sprints
Features Remaining at end of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 30		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 06
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	3
Day 1 Left	2	1
Day 2 Left	2	0
Day 3 Left	2	0
Day 4 Left	2	0
Day 5 Left	2	0
Day 6 Left	2	0
Day 7 Left	2	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2	#REF!		Create main_window.cpp *.h files, add main window, menubar, menuitem – file and exit	Completed Day 1
3	#REF!		Start a new game by clicking new game button
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Nov 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 13
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	3
Day 1 Left	3	0
Day 2 Left	3	0
Day 3 Left	2	1
Day 4 Left	2	0
Day 5 Left	2	0
Day 6 Left	0	2
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	#REF!		Make 8x8 buttons of alternating colors and show it in main window	Completed Day 3
2	#REF!		See location/icon of each piece on board	Completed Day 6
3	#REF!		Make classes of queen, bishop, pawn, king, knight and rook with overridden move method	Completed Day 6
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 20
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	6
Day 1 Left	6	0
Day 2 Left	6	0
Day 3 Left	6	0
Day 4 Left	5	1
Day 5 Left	3	2
Day 6 Left	1	2
Day 7 Left	0	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	#REF!		Select a piece to move by tracking the first click in Board class	Completed Day 4
2	#REF!		Select empty square to move piece to. Update the piece location to selected square	Completed Day 5
3	#REF!		Make a tool button which clears the first click	Completed Day 5
4	#REF!		Check if piece is opponents, then delete the opp. Piece and change location of player’s piece	Completed Day 6
5	#REF!		Write whose turn it is in status bar	Completed Day 6
6	#REF!		Turn status bar red with ‘Illegal move’ text to warn player	Completed Day 7
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 20		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 27
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	0	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	#REF!		Perform a passing capture by pawn, change move method of pawn	Completed Day 7
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks